## How to use
Step | What to do
1. Start here | Work through the Before launch sheet from top to bottom. The areas are ordered by risk: indexing and structure first, then pages, content, speed, mobile, analytics and legal basics.
2. One row, one check | Do what the “How to check” column says and compare what you see with the “Check” column. Sample one page of each type (home, category, product or service, article, contact), not every page.
3. Set the status | Not started: nobody has looked yet. In progress: a problem was found and is being fixed. Done: checked and correct. Not applicable: the row does not concern this site.
4. Write a note | Record what you found, the date and who fixes it. The notes that begin with “Example:” show the format; replace them with your own.
5. Launch blockers | Do not go public with open rows in Indexing or Structure: a blocked or broken site cannot be read by search engines. Other areas can be finished during the first week.
6. Relaunch rows | Rows that begin with “Relaunch only” or “Domain change only” are for a rebuilt or moved site. For a brand-new site set them to Not applicable.
7. After launch | Switch to the First month sheet and follow the “When” column: launch day, week 1, week 2, weeks 3–4.
8. Progress rows | The rows named Progress at the bottom of each check sheet count statuses with formulas. Do not type over them. To add your own check, insert a row between existing checks, not below the last one.
9. Tools you need | A browser with developer tools (Chrome DevTools), Google Search Console, PageSpeed Insights (pagespeed.web.dev) and Google's Rich Results Test.
10. What this file is not | It is a readiness check on a sample of pages. It does not replace a full technical audit or a review of content quality, and a finished list says nothing about positions in search.
11. Sources | The checks follow Google Search Central and Search Console help pages read on 2026-10-04. Menus change: if a report name differs, look it up in the tool's help.

## Before launch
Area | Check | How to check | Why it matters | Status | Note
Indexing | robots.txt on the live domain has no site-wide block left from development | Open https://example.com/robots.txt in a private browser window. Under User-agent: * there must be no line “Disallow: /”. Only folders you really want uncrawled (admin, cart, internal search) may be listed. | A leftover “Disallow: /” stops crawlers from reading every page. | Not started | Example: staging rule “Disallow: /” found and removed on launch day.
Indexing | Pages meant for search carry no noindex | Open the page source (Ctrl+U) of the home page and of one page of each type and search for “noindex”. Then open DevTools > Network, click the first row and look for an X-Robots-Tag response header. | When Google crawls a page with noindex, it drops the page from results. | Not started
Indexing | Pages that must stay out of search use noindex or a login, not robots.txt | List thank-you pages, account pages, internal search and test pages. Each needs a noindex tag or a password and must not be disallowed in robots.txt, otherwise the crawler never sees the noindex. | A URL blocked only in robots.txt can still appear in results, without a description. | Not started
Indexing | CSS, JavaScript and image folders are not blocked | Read every Disallow line in robots.txt. None should cover the folders that hold styles, scripts or images. After launch confirm it in Search Console: URL Inspection > Test live URL > View tested page > Screenshot. | Google needs the same resources as a browser to understand a page. | Not started
Indexing | Every important page answers with HTTP 200 | Open DevTools > Network, reload the page and read the status of the first row. Test the home page, a category, a product or service page, an article and the contact page. | Google indexes only pages served with a 200 status. Error pages are not indexed. | Not started
Indexing | The XML sitemap lists only the pages you want in search | Open https://example.com/sitemap.xml. Every URL must be absolute, start with https and be the final address: no redirects, no noindex pages, no test or staging URLs. One file holds up to 50,000 URLs or 50 MB. | The sitemap tells search engines which URLs you consider important. It is a hint, not an order. | Not started
Indexing | robots.txt points to the sitemap | Look for a line such as “Sitemap: https://example.com/sitemap.xml” in robots.txt. The address must be complete, with https and the right host. | Crawlers pick the sitemap up the next time they read robots.txt. | Not started
Indexing | The Search Console property is created and ownership is verified | Add the site in Google Search Console. A Domain property, verified with a DNS record, covers http, https and all subdomains. Wait until the property shows as verified. | Without verification you cannot see the indexing reports or receive alerts about problems. | Not started
Structure | One address version: http, https, www and non-www all end on the same URL | Type all four variants of the home page into the browser. Each must land on one final address in a single redirect. Repeat for one inner page. | A redirect is a strong signal of which URL should be shown. Without it the same page lives at several addresses. | Not started | Example: the http://www version answered 200 instead of redirecting; fixed in the server settings.
Structure | The HTTPS certificate is valid for the exact host and pages load no http resources | Click the icon to the left of the address in Chrome and read the connection details. Then open DevTools > Console and look for Mixed Content warnings. | Google prefers the HTTPS version as canonical unless the certificate is invalid or the page pulls in insecure resources. | Not started
Structure | Each page has a rel="canonical" that points to itself with a full URL | In the page source search for “canonical”. The href must be the absolute https address of this same page on the live domain, inside <head>. A staging domain here is a launch error. | The canonical link is a strong signal of which URL you prefer. A wrong one sends that signal to the wrong address. | Not started
Structure | Menu and in-page links are real links | Right-click a menu item > Inspect. You should see an <a> element with an href that holds a real address, not a button or a span that only works through a script. | Google can generally crawl a link only when it is an <a> element with an href attribute. | Not started
Structure | Every page you care about is linked from at least one other page | Take the URL list from the sitemap. For each important page find a link to it in the menu, in a category or in a related block. A site crawler's report of pages without incoming links does this faster. | Search engines discover pages mainly by following links. | Not started
Structure | A missing page returns a real 404 | Open a made-up address such as https://example.com/no-such-page-123. The page should say it was not found and offer a way back, and DevTools > Network must show status 404, not 200 and not a redirect to the home page. | A “not found” page that answers 200 is reported as a soft 404. | Not started
Structure | Relaunch only: every old URL has a mapped new URL and a permanent redirect | Collect old URLs from the old sitemap, analytics and Search Console. Put old and new addresses side by side. Test a sample: each old URL must answer 301 or 308 and land on the matching page in one step, not on the home page. | A permanent server-side redirect tells Google the page has moved. Sending many old URLs to the home page may be treated as a soft 404. | Not started
Pages | Every page has its own descriptive <title> | Check each page type in the source or in the browser tab. No empty titles, no bare “Home”, no identical titles on different pages. A crawler export sorted by title shows duplicates quickly. | The <title> element is one of the main sources Google uses for the headline of a result. | Not started
Pages | Key pages have a unique meta description | In the source find <meta name="description">. The home page and the main landing pages need their own one or two sentence summary, not the same text everywhere. | Google may use it as the snippet when it describes the page better than the page text does. | Not started
Pages | Each page has one clear main heading | Look at the page as a visitor. One heading should stand out as the title of the page, usually the first <h1>, and it should say the same thing as the <title>. | When it is unclear which text is the main title, Google may build the result headline from something else. | Not started
Pages | Structured data, if you use it, passes the Rich Results Test | Paste the page address or the code into Google's Rich Results Test and fix the errors. Check that the markup describes only what a visitor can see on that page. | A rich result needs all required properties, and templates can break after deployment. | Not started
Pages | The home page declares a favicon | In the home page source find <link rel="icon" href="...">. Open the file: it should be square and larger than 48x48 px, and its address must not be blocked in robots.txt. | Google can show the favicon next to your result only if it can crawl the file. | Not started
Content | No placeholder or test content is published | Search the site and the CMS for “lorem”, “test”, “example” and sample products. Click every menu and footer link once. | Anything public can be crawled as soon as the site is live. | Not started
Content | No two pages say the same thing | Compare near-identical pages: city or service variants, print versions, filtered lists. Merge them, redirect the spare one or set a canonical to the main page. | With the same content on several URLs, search engines pick one address themselves and spend crawling on the rest. | Not started
Content | Images that carry meaning have alt text | Right-click key images > Inspect and read the alt attribute. It should describe the picture in plain words. Images used as links need alt text too. | Alt text helps search engines understand an image. For an image link Google uses it as the link text. | Not started
Content | Link text says where the link leads | Read only the linked words on the main pages. Replace “click here” and bare “read more” on important links with a few words that name the target page. | Link text tells people and Google what the linked page is about. | Not started
Speed | The main page types are tested in PageSpeed Insights, mobile tab | Run pagespeed.web.dev for the home page and one page of each main type and write down LCP and CLS from the lab test. Reference points for real-user data: LCP within 2.5 s, INP under 200 ms, CLS under 0.1. | Core Web Vitals measure loading, responsiveness and visual stability. A new site has lab data only. | Not started
Speed | No oversized images or files on key pages | DevTools > Network > Img, sort by size. Nothing should be far heavier than its display size needs. Check that images have width and height set so the layout does not jump while loading. | Loading speed and layout stability are two of the three Core Web Vitals. | Not started
Mobile | Key pages are usable on a phone | Open them on a real phone or in Chrome DevTools device mode. Text is readable without zooming, nothing scrolls sideways, buttons and the menu can be tapped. | Google indexes and ranks using the mobile version of the content. | Not started
Mobile | The phone view carries the same content as the desktop view | Compare main text, headings, title, description and structured data in both views. Content moved into tabs or accordions is fine. Content removed on small screens is not. | Only the content shown on the mobile version is used for indexing. | Not started
Mobile | No pop-up covers the whole page on arrival | Open a page on a phone in a private window. A consent banner required by law is fine. A promotional overlay should be a small banner instead. | Full-page overlays make content hard to reach for visitors and for search engines. | Not started
Analytics | Analytics code is on every page type and records a visit | Open the site in a normal window and watch the real-time report of your analytics tool. Visit the home page, an inner page and the thank-you page. | Without data from day one you cannot tell what the launch changed. | Not started
Analytics | Key actions are recorded | Send a test form, click the phone number, place a test order. Each action must appear in analytics as an event or a goal. | Visits alone do not show which pages bring enquiries. | Not started
Analytics | Relaunch only: a baseline of the old site is saved | Export queries and pages for the last three months from the Search Console Performance report, and the top landing pages from analytics. Keep the files. | You will need the old numbers to judge the new site. | Not started
Legal basics | The legal pages your situation requires are published and linked in the footer | Open the footer links: privacy policy, terms, and a cookie or consent notice where your visitors' country requires one. Check that the consent choice really switches analytics on and off. | Requirements depend on the country and the business. This row is a reminder, not legal advice: ask a lawyer what applies to you. | Not started
Legal basics | Company and contact details are real, visible and the same everywhere | Compare name, address, phone and opening hours on the contact page, in the footer, in structured data and in your business listings. | Visitors and search engines should meet one consistent set of details. | Not started
Progress | Done |  | Number of checks with this status (counted by formula)
Progress | In progress |  | Number of checks with this status (counted by formula)
Progress | Not started |  | Number of checks with this status (counted by formula)
Progress | Not applicable |  | Number of checks with this status (counted by formula)
Progress | Done, % of applicable rows |  | Rows marked Not applicable are left out of the total

## First month
When | Check | How to check | Why it matters | Status | Note
Launch day | Live robots.txt and noindex checked again | Repeat the first two rows of the Before launch sheet on the live domain. In Search Console open the robots.txt report and confirm that the file was fetched. | Google lists leftover noindex and robots.txt blocks among the common mistakes of a site move. | Not started | Example: live robots.txt checked at 10:00, no blocks; noindex absent on five page types.
Launch day | Sitemap submitted | Search Console > Sitemaps: enter the sitemap address and submit. Come back in a few days: the status should read Success. “Couldn't fetch” or “Has errors” needs a fix and a new submission. | The report shows when the file was read and what went wrong. Submitting is a hint, not an order to index. | Not started
Launch day | Home page inspected and indexing requested | Search Console > URL Inspection: enter the home page and click Test live URL. Page fetch should be Successful and the screenshot should look like the real page. Then click Request indexing. | For a new site, Search Console help names an indexing request for the home page as the best first step. | Not started
Launch day | Relaunch only: redirects tested on the live site | Take 20 old URLs from your map, including the most visited. Each must answer 301 or 308 and land on the matching new page in one step. Check that internal links already use the new addresses. | Google says it frequently sees redirects that point to wrong or non-existent pages after a move. | Not started
Launch day | Domain change only: Change of Address submitted | In Search Console open the old property and use the Change of Address tool. It is not needed for a move from http to https, between www and non-www, or between paths on the same domain. | The tool tells Google about a move from one domain or subdomain to another. | Not started
Week 1 | The site shows up for a site: search | Search Google for site:example.com, then for the exact address of two or three key pages. A handful of results is enough at this stage. If nothing appears after the first couple of weeks, go to the next row. | Search Console help says it can take a week or so before a new site starts to be crawled and indexed. | Not started
Week 1 | Reasons for pages not being indexed are read one by one | Search Console > Page indexing. In the table “Why pages aren't indexed” open each reason: URL marked ‘noindex’, URL blocked by robots.txt, Not found (404), Soft 404, Page with redirect. Decide whether each one is intended. For a site under 500 pages Google says the site: search above is usually enough. | Not-indexed URLs are fine when the reason is expected. Your important pages should be in the indexed group. | Not started
Week 1 | Server errors and missing pages | In the same report open Server error (5xx) and Not found (404). Fix the cause, or redirect removed pages that have a replacement. On a site of a thousand pages or more also open Property settings > Crawl stats and read Host status. | Pages that answer 4xx are not indexed, and repeated 5xx errors make Google crawl more slowly. | Not started
Week 1 | Broken internal links | Crawl the live site with a link checker or click through the main paths. Fix links that lead to 404 pages. After a relaunch replace links that still pass through a redirect with the final address. | Links are how people and crawlers reach pages, and Google advises updating internal links after a move. | Not started
Week 2 | Google's canonical matches yours on key pages | Run URL Inspection on five important pages. Under Page indexing compare User-declared canonical with Google-selected canonical. A different address means conflicting signals: check redirects, canonical tags and the sitemap. | Google may choose another URL when the signals disagree. | Not started
Week 2 | No manual actions or security issues | Search Console > Manual actions and Security issues: both should report no issues. Check that Search Console emails reach an inbox somebody reads. | With a manual action, some or all of the site is not shown in results. | Not started
Week 2 | Structured data reports are clean | If the site has markup, open the rich result reports under Enhancements in Search Console once they appear. Open each invalid item type and fix the template. | Markup that validated before launch can break in a live template. | Not started
Weeks 3–4 | Queries begin to appear | Search Console > Performance > Queries tab, with the date range starting on launch day. Note which queries and pages collect impressions and whether your brand name and main services are among them. Do not judge positions yet. | The report shows whether Google connects your pages with the topics you expect. | Not started
Weeks 3–4 | Real-user speed data | Open the Core Web Vitals report for mobile and desktop. “No data available” is normal for a new or low-traffic site. If there is data, open the groups marked Poor or Need improvement and test an example URL in PageSpeed Insights. | Field data comes from real visits over the previous 28 days and can differ from the lab test done before launch. | Not started
Weeks 3–4 | Relaunch only: old and new numbers compared | Put clicks and impressions of the top pages next to the saved baseline. Check in the Page indexing report that new URLs are entering the index. Keep the redirects in place for at least a year. | Google says a small or medium site can take a few weeks for most pages to move, and that visibility may fluctuate meanwhile. | Not started
Progress | Done |  | Number of checks with this status (counted by formula)
Progress | In progress |  | Number of checks with this status (counted by formula)
Progress | Not started |  | Number of checks with this status (counted by formula)
Progress | Not applicable |  | Number of checks with this status (counted by formula)
Progress | Done, % of applicable rows |  | Rows marked Not applicable are left out of the total